## BF2 Timeline
| ACTION |  | DATE |  | PLACE | ORGANIZER
1 | Dance Media BF | Dance Media BF - Video Source | 01/06/2012 | 31/05/2014 | UK, Greenwich and other partner countries | Greenwich Dance
2 | DCL Event | DCL Event | 01/06/2012 | 5/06/2012 | HR, Zagreb | HIPP
3 | Performance BF | Performance BF | 01/06/2012 | 5/06/2012 | HR, Zagreb | HIPP
4 | Dialogue BF | Dialogue BF | 01/06/2012 | 5/06/2012 | HR, Zagreb | HIPP
5 | Creation Beyond Front@ IV audition | Creation Beyond Front@ IV audition | 01/06/2012 | 5/06/2012 | HR, Zagreb | HIPP
| Festival | Big Dance 2012 / Greenwich Dance Festival 2012 | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
6 | DCL in Progress | DCL in Progress | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
7 | DCL Event | DCL Event | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
8 | Dialogue BF | Dialogue BF | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
9 | Co-organiser meeting | London (partial) | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
10 | Creation Beyond Front@ IV Audition | Creation Beyond Front@ IV Audition | 21/08/2012 | 24/08/2012 | HU, Budapest | Pro-Progressione
| Festival | Front@ Contemporary Dance Festival 2012 | 24/08/2012 | 01/09/2012 | SI, Murska Sobota | Flota
11 | Creation Beyond Front@ IV Audition | Creation Beyond Front@ IV Audition | 23/08/2012 | 01/09/2012 | SI, Murska Sobota | Flota
12 | Dance Media BF | Dance Media BF | 24/08/2012 | 01/09/2012 | SI, Murska Sobota | Flota
13 | Performance BF | Performance BF | 24/08/2012 | 01/09/2012 | SI, Murska Sobota | Flota
14 | DCL in Progress | DCL in Progress | 24/08/2012 | 01/09/2012 | SI, Murska Sobota | Flota
15 | DCL Event | DCL Event | 24/08/2012 | 01/09/2012 | SI, Murska Sobota | Flota
16 | Dialogue BF | Dialogue BF | 24/08/2012 | 01/09/2012 | SI, Murska Sobota | Flota
17 | Co-organiser meeting | MS | 24/08/2012 | 01/09/2012 | SI, Murska Sobota | Flota
18 | Audience BF | OHO to MS | 24/08/2012 | 01/09/2012 | AT, Oberwart | OHO
18 | Audience BF | DID to Ms | 24/08/2012 | 01/09/2012 | AT, Pinkafeld | D.ID
18 | Audience BF | Zagreb to Murska Sobota | 24/08/2012 | 01/09/2012 | HR, Zagreb / SI, Murska Sobota | HIPP
18 | Audience BF | from Nagykanizsa to MS | 24/08/2012 | 01/09/2012 | HU, Nagykanizsa / SI, Murska Sobota | Pro-Progressione
19 | DCL in Progress | DCL in Progress | 01/10/2012 | 15/10/2012 | HR, Zagreb | HIPP
20 | Creation Beyond Front@ IV | Creation Beyond Front@ IV rehearsal | 01/10/2012 | 15/10/2012 | HR, Zagreb | HIPP
21 | DCL in Progress | DCL in Progress | 16/01/2013 | 28/02/2013 | AT, Pinkafeld | D.ID
22 | Co-organiser meeting | MS | 16/03/2013 | 17/03/2013 | SI, Murska Sobota | Flota
23 | Dialogue BF | Dialogue BF | 17/03/2013 | 18/03/2013 | SI, Murska Sobota | Flota
| Festival | Burgenlandische Tanztage-Oberwart 2013 | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
24 | Performance BF | Performance BF | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
25 | DCL Event | DCL Event | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
26 | Creation Beyond Front@ IV | Creation Beyond Front@ IV Pre-premiere | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
27 | Community | Community Beyond Front@ | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
28 | Dialogue BF | Dialogue BF | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
29 | Audience BF | Bus to Oberwart from MS | 09/05/2013 | 13/05/2013 | SI, Murska Sobota | Flota
29 | Audience BF | from Zagreb to Oberwart | 09/05/2013 | 13/05/2013 | HR, Zagreb | HIPP
30 | DCL Event | DCL Event | 22/05/2013 | 26/05/2013 | HU, Veszprém | Pro-Progressione
31 | Creation Beyond Front@ IV | Creation Beyond Front@ IV performance | 24/05/2013 | 24/05/2013 | HU, Veszprem | Pro-Progressione
32 | Dialogue BF | Dialogue BF | 26/05/2013 | 26/05/2013 | HU, Veszprem | Pro-Progressione
33 | Audience BF | Bus from AT to Veszprém | 23/05/2013 | 23/05/2013 | AT, Oberwart to HU, Veszprém | OHO
33 | Audience BF | Bus from SI to Veszprém | 23/05/2013 | 23/05/2013 | SI, Murska Sobota to HU, Veszprém | Flota
| Festival | Dance Week Festival 2013 | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
34 | Creation Beyond Front@ IV | Creation Beyond Front@ IV Premiere | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
35 | DCL Event | DCL Event | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
36 | Performance BF | Performance BF | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
37 | Dialogue BF | Dialogue BF | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
38 | Co-organiser meeting | ZG | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
39 | Audience BF | Bus to Zagreb | 01/06/2013 | 01/06/2013 | AT, Oberwart | OHO
39 | Audience BF | Bus to Zagreb | 28/05/2013 | 28/05/2013 | SI, Murska Sobota | Flota
39 | Audience BF | from HU to Zagreb | 2013-05-28 | 02/06/2013 | HU, Budapest | Pro-Progressione
40 | Creation Beyond Front@ V | Creation Beyond Front@ V - production period 1 | 01/07/2013 | 15/07/2013 | AT, Pinkafeld | D.ID
41 | Creation Beyond Front@ V | Creation Beyond Front@ V - production period 2 | 16/07/2013 | 11/08/2013 | HU, Budapest | Pro-Progressione
| Festival | Front@ Contemporary Dance Festival 2013 | 27/08/2013 | 31/08/2013 | SI, Murska Sobota | Flota
42 | Dance Media BF | Dance Media BF | 27/08/2013 | 31/08/2013 | SI, Murska Sobota | Flota
43 | Performance BF | Performance BF | 27/08/2013 | 31/08/2013 | SI, Murska Sobota | Flota
44 | DCL Event | DCL Event | 27/08/2013 | 31/08/2013 | SI, Murska Sobota | Flota
45 | Creation Beyond Front@ IV | Creation Beyond Front@ IV | 27/08/2013 | 31/08/2013 | SI, Murska Sobota | Flota
46 | Creation Beyond Front@ V | Creation Beyond Front@ V - Premiere | 27/08/2013 | 31/08/2013 | SI, Murska Sobota | Flota
47 | Dialogue BF | Dialogue BF | 27/08/2013 | 31/08/2013 | SI, Murska Sobota | Flota
48 | Co-organiser meeting | Murska Sobota | 27/08/2013 | 31/08/2013 | SI, Murska Sobota | Flota
49 | Audience BF | OHO to MS | 27/08/2013 | 31/08/2013 | AT, Oberwart | OHO
49 | Audience BF | Bus from Zagreb to MS | 27/08/2013 | 31/08/2013 | HR, Zagreb | HIPP
49 | Audience BF | from Nagykanizsa to MS | 27/08/2013 | 31/08/2013 | HU, Nagykanizsa | Pro-Progressione
50 | Co-organiser meeting | London | 29/09/2013 | 30/09/2013 | UK, Greenwich | Greenwich Dance
51 | Creation Beyond Front@ IV | Creation Beyond Front@ IV Performance | 14/11/2013 | 14/11/2013 | HR, Zagreb | HIPP
52 | Creation Beyond Front@ V | Creation Beyond Front@ V performance | 16/11/2013 | 16/11/2013 | HR, Zagreb | HIPP
53 | DCL Event | DCL Event | 15/11/2013 | 15/11/2013 | HR, Zagreb | HIPP
54 | Dialogue BF | Dialogue BF | 15/11/2013 | 15/11/2013 | HR, Zagreb | HIPP
55 | Audience BF | bus from Oberwart to ZG | 2013-11-15 | 2013-11-15 | AT, Oberwart | OHO
56 | Co-organiser meeting | Murska Sobota | 22/02/2014 | 24/02/2014 | SI, Murska Sobota | Flota
57 | Creation Beyond Front@ V | Creation Beyond Front@ V - rehearsal period for reprises | 2014-04-21 | 28/04/2014 | AT, Pinkafeld | D.ID
| Festival | Burgenlandische Tanztage-Oberwart 2014 | 08/05/2014 | 11/05/2014 | AT, Oberwart | OHO
58 | DCL Event | DCL Event | 08/05/2014 | 11/05/2014 | AT, Oberwart | OHO
59 | Performance BF | Performance BF | 08/05/2014 | 11/05/2014 | AT, Oberwart | OHO
60 | Creation Beyond Front@ V | Creation Beyond Front@ V | 08/05/2014 | 11/05/2014 | AT, Oberwart | OHO
61 | Community | Community Beyond Front@ | 08/05/2014 | 11/05/2014 | AT, Oberwart | D.ID
62 | Dialogue BF | Dialogue BF | 08/05/2014 | 11/05/2014 | AT, Oberwart | D.ID
63 | Audience BF | Bus to Oberwart | 23/05/2014 | 11/05/2014 | SI, Murska Sobota | Flota
63 | Audience BF | from HU to Oberwart | 08/05/2014 | 11/05/2014 | HU, Budapest | Pro-Progressione
| Festival | MonoDance Festival 2014 | 2014-05-10 | 17/05/2014 | HU, Budapest | Pro-Progressione
64 | DCL in Progress | DCL in Progress | 2014-05-13 | 18/05/2014 | HU Budapest | Pro-Progressione
65 | DCL Event | DCL Event | 2014-05-10 | 17/05/2014 | HU, Budapest | Pro-Progressione
66 | Performance BF | Performance BF Budapest | 2014-05-10 | 17/05/2014 | HU, Budapest | Pro-Progressione
67 | Creation Beyond Front@ V | Creation Beyond Front@ V performance | 2014-05-13 | 18/05/2014 | HU, Budapest | Pro-Progressione
68 | Audience BF | Bus to Budapest | 13/05/2014 | 18/05/2014 | AT, Oberwart | OHO
68 | Audience BF |  | 11/05/2014 | 11/05/2014 | HR, Zagreb | HIPP
68 | Audience BF | Bus to Budapest | 11/05/2014 | 11/05/2014 | SI, Murska Sobota | Flota
| Festival | Dance Week Festival 2014 | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
69 | DCL Event | DCL Event | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
70 | Performance BF | Performance BF | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
71 | Dialogue BF | Dialogue BF | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
72 | Co-organiser meeting | Zagreb -Evaluation and Ending of Phase II | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
73 | Audience BF | Bus to Zagreb | 24/05/2014 | 31/05/2014 | SI, Murska Sobota | Flota
73 | Audience BF | Bus to Zagreb | 24/05/2014 | 31/05/2014 | AT, Oberwart | OHO
Note on D89: ksenija: sometime between 4. and 8.6.
Note on D90: ksenija: sometime between 4. and 8.6.
Note on D91: ksenija: sometime between 4. and 8.6.
Note on D92: ksenija: sometime between 4. and 8.6.
Note on D93: ksenija: sometime between 4. and 8.6.
Note on D94: ksenija: sometime between 4. and 8.6.
Note on D95: ksenija: sometime between 4. and 8.6.

## GDA
Dance Media BF | Dance Media BF - Video Source | 01/06/2012 | 31/05/2014 | UK, Greenwich and other partner countries | Greenwich Dance
Festival | Big Dance 2012 / Greenwich Dance Festival 2012 | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
DCL in Progress | DCL in Progress | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
DCL Event | DCL Event | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
Dialogue BF | Dialogue BF | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
Co-organiser meeting | London (partial) | 18/06/2012 | 21/06/2012 | UK, Greenwich | Greenwich Dance
Co-organiser meeting | London | 29/09/2013 | 30/09/2013 | UK, Greenwich | Greenwich Dance

## HIPP
DCL Event | DCL Event | 01/06/2012 | 5/06/2012 | HR, Zagreb | HIPP
Performance BF | Performance BF | 01/06/2012 | 5/06/2012 | HR, Zagreb | HIPP
Dialogue BF | Dialogue BF | 01/06/2012 | 5/06/2012 | HR, Zagreb | HIPP
Creation Beyond Front@ IV audition | Creation Beyond Front@ IV audition | 01/06/2012 | 5/06/2012 | HR, Zagreb | HIPP
Audience BF | Zagreb to Murska Sobota | 24/08/2012 | 01/09/2012 | HR, Zagreb / SI, Murska Sobota | HIPP
DCL in Progress | DCL in Progress | 01/10/2012 | 15/10/2012 | HR, Zagreb | HIPP
Creation Beyond Front@ IV | Creation Beyond Front@ IV rehearsal | 01/10/2012 | 15/10/2012 | HR, Zagreb | HIPP
Audience BF | from Zagreb to Oberwart | 09/05/2013 | 13/05/2013 | HR, Zagreb | HIPP
Festival | Dance Week Festival 2013 | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
Creation Beyond Front@ IV | Creation Beyond Front@ IV Premiere | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
DCL Event | DCL Event | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
Performance BF | Performance BF | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
Dialogue BF | Dialogue BF | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
Co-organiser meeting | ZG | 28/05/2013 | 02/06/2013 | HR, Zagreb | HIPP
Audience BF | Bus from Zagreb to MS | 27/08/2013 | 31/08/2013 | HR, Zagreb | HIPP
Creation Beyond Front@ IV | Creation Beyond Front@ IV Performance | 14/11/2013 | 14/11/2013 | HR, Zagreb | HIPP
Creation Beyond Front@ V | Creation Beyond Front@ V performance | 16/11/2013 | 16/11/2013 | HR, Zagreb | HIPP
DCL Event | DCL Event | 15/11/2013 | 15/11/2013 | HR, Zagreb | HIPP
Dialogue BF | Dialogue BF | 15/11/2013 | 15/11/2013 | HR, Zagreb | HIPP
Audience BF | Bus from Zagreb to Budapest | 11/05/2014 | 11/05/2014 | HR, Zagreb | HIPP
Festival | Dance Week Festival 2014 | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
DCL Event | DCL Event | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
Performance BF | Performance BF | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
Dialogue BF | Dialogue BF | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
Co-organiser meeting | Zagreb -Evaluation and Ending of Phase II | 24/05/2014 | 31/05/2014 | HR, Zagreb | HIPP
Note on C21: ksenija: sometime between 4. and 8.6.
Note on C22: ksenija: sometime between 4. and 8.6.
Note on C23: ksenija: sometime between 4. and 8.6.
Note on C24: ksenija: sometime between 4. and 8.6.
Note on C25: ksenija: sometime between 4. and 8.6.

## PRO-PROG
Creation Beyond Front@ IV Audition | Creation Beyond Front@ IV Audition | 21/08/2012 | 24/08/2012 | HU, Budapest | Pro-Progressione
Audience BF | from Nagykanizsa to MS | 24/08/2012 | 01/09/2012 | HU, Nagykanizsa / SI, Murska Sobota | Pro-Progressione
DCL Event | DCL Event | 22/05/2013 | 26/05/2013 | HU, Veszprém | Pro-Progressione
Creation Beyond Front@ IV | Creation Beyond Front@ IV performance | 24/05/2013 | 24/05/2013 | HU, Veszprem | Pro-Progressione
Dialogue BF | Dialogue BF | 26/05/2013 | 26/05/2013 | HU, Veszprem | Pro-Progressione
Audience BF | from HU to Zagreb | 2013-05-28 | 02/06/2013 | HU, Budapest | Pro-Progressione
Creation Beyond Front@ V | Creation Beyond Front@ V - production period 2 | 16/07/2013 | 11/08/2013 | HU, Budapest | Pro-Progressione
Audience BF | from Nagykanizsa to MS | 27/08/2013 | 31/08/2013 | HU, Nagykanizsa | Pro-Progressione
Audience BF | from HU to Oberwart | 08/05/2014 | 11/05/2014 | HU, Budapest | Pro-Progressione
Festival | MonoDance Festival 2012 | 2014-05-10 | 17/05/2014 | HU, Budapest | Pro-Progressione
DCL in Progress | DCL in Progress | 2014-05-13 | 18/05/2014 | HU Budapest | Pro-Progressione
DCL Event | DCL Event | 2014-05-10 | 17/05/2014 | HU, Budapest | Pro-Progressione
Performance BF | Performance BF Budapest | may 2014 | may 2014 | HU, Budapest | Pro-Progressione
Creation Beyond Front@ V | Creation Beyond Front@ V performance | 2014-05-13 | 18/05/2014 | HU, Budapest | Pro-Progressione

## FLOTA
Festival | Front@ Contemporary Dance Festival 2012 | 24/08/2012 | 01/09/2012
Creation Beyond Front@ IV Audition | Creation Beyond Front@ IV Audition | 23/08/2012 | 01/09/2012 | up to us - slovenska in hrvaška avdicija
Dance Media BF | Dance Media BF | 24/08/2012 | 01/09/2012
Performance BF | Performance BF | 24/08/2012 | 01/09/2012
DCL in Progress | DCL in Progress | 24/08/2012 | 01/09/2012
DCL Event | DCL Event | 24/08/2012 | 01/09/2012 | 25.8 - 1. 9.
Dialogue BF | Dialogue BF | 24/08/2012 | 01/09/2012 | CCP 27.
Co-organiser meeting | MS | 24/08/2012 | 01/09/2012 | 31. 8. 10.00
Co-organiser meeting | MS | 16/03/2013 | 17/03/2013
Dialogue BF | Dialogue BF | 17/03/2013 | 18/03/2013
Audience BF | Bus to Oberwart from MS | 09/05/2013 | 13/05/2013
Audience BF | Bus from SI to Veszprém | 23/05/2013 | 23/05/2013
Audience BF | Bus to Zagreb | 28/05/2013 | 28/05/2013
Festival | Front@ Contemporary Dance Festival 2013 | 27/08/2013 | 31/08/2013
Dance Media BF | Dance Media BF | 27/08/2013 | 31/08/2013
Performance BF | Performance BF | 27/08/2013 | 31/08/2013
DCL Event | DCL Event | 27/08/2013 | 31/08/2013
Creation Beyond Front@ IV | Creation Beyond Front@ IV | 27/08/2013 | 31/08/2013
Creation Beyond Front@ V | Creation Beyond Front@ V - Premiere | 27/08/2013 | 31/08/2013
Dialogue BF | Dialogue BF | 27/08/2013 | 31/08/2013
Co-organiser meeting | Murska Sobota | 27/08/2013 | 31/08/2013
Co-organiser meeting | Murska Sobota | 22/02/2014 | 24/02/2014
Audience BF | Bus to Oberwart | 23/05/2014 | 11/05/2014
Audience BF | Bus to Budapest | 11/05/2014 | 11/05/2014
Audience BF | Bus to Zagreb | 24/05/2014 | 31/05/2014

## OHO
Audience BF | OHO to MS | 24/08/2012 | 01/09/2012 | AT, Oberwart | OHO
Festival | Burgenlandische Tanztage-Oberwart 2013 | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
Performance BF | Performance BF | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
DCL Event | DCL Event | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
Creation Beyond Front@ IV | Creation Beyond Front@ IV Pre-premiere | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
Community | Community Beyond Front@ | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
Dialogue BF | Dialogue BF | 09/05/2013 | 13/05/2013 | AT, Oberwart | OHO
Audience BF | Bus from AT to Veszprém | 23/05/2013 | 23/05/2013 | AT, Oberwart to HU, Veszprém | OHO
Audience BF | Bus to Zagreb | 01/06/2013 | 01/06/2013 | AT, Oberwart | OHO
Audience BF | OHO to MS | 27/08/2013 | 31/08/2013 | AT, Oberwart | OHO
Audience BF | bus from Oberwart to ZG | 2013-11-15 | 2013-11-15 | AT, Oberwart | OHO
Festival | Burgenlandische Tanztage-Oberwart 2014 | 08/05/2014 | 11/05/2014 | AT, Oberwart | OHO
DCL Event | DCL Event | 08/05/2014 | 11/05/2014 | AT, Oberwart | OHO
Performance BF | Performance BF | 08/05/2014 | 11/05/2014 | AT, Oberwart | OHO
Creation Beyond Front@ V | Creation Beyond Front@ V | 08/05/2014 | 11/05/2014 | AT, Oberwart | OHO
Audience BF | Bus to Budapest | 13/05/2014 | 18/05/2014 | AT, Oberwart | OHO
Audience BF | Bus to Zagreb | 24/05/2014 | 31/05/2014 | AT, Oberwart | OHO
Note on C17: ksenija: sometime between 4. and 8.6.

## D.ID
Audience BF | DID to Ms | 24/08/2012 | 01/09/2012 | AT, Pinkafeld | D.ID
DCL in Progress | DCL in Progress | 16/01/2013 | 28/02/2013 | AT, Pinkafeld | D.ID
Creation Beyond Front@ V | Creation Beyond Front@ V - production period 1 | 01/07/2013 | 15/07/2013 | AT, Pinkafeld | D.ID
Creation Beyond Front@ V | Creation Beyond Front@ V - rehearsal period for reprises | 2014-04-21 | 28/04/2014 | AT, Pinkafeld | D.ID
Community | Community Beyond Front@ | 08/05/2014 | 11/05/2014 | AT, Oberwart | D.ID
Dialogue BF | Dialogue BF | 08/05/2014 | 11/05/2014 | AT, Oberwart | D.ID